## Matrix
Village of Deferiet
DOS Nomination Study
Implementation Matrix
|  | Description and Next Steps | Project Champion | Potential Partners | Potential Funding | Immediate (1-2 yrs) | Short-Term (3-5 yrs) | Long-Term (6-10 yrs) | Ongoing | Notes
Policy Area 1: Environmental
Goal 1: Decrease threats to environmental and human health.
1 | Remediate/redevelop the former General Store/Post Office building located on Anderson Avenue. | Utilize Restore NY grant monies to secure and remediate the former Post Office building located at 45 Anderson Avenue. | Deferiet Redevelopment Corporation (DRC) | Village of Deferiet, Town of Wilna, NYS Empire State Development (ESD), Jefferson County | Restore NY | H
2 | Continue to partner with the U.S. Environmental Protection Agency (EPA). | Work closely with the EPA to: • Continue to secure monies for Phase 1 and Phase 2 assessments of brownfield sites throughout the BOA. • Secure money for clean-up and remediation of strategic brownfield sites. | DRC | U.S. Environmental Protection Agency (EPA), Village, Town | EPA, Jefferson County Economic Development (JCED), Jefferson Co. (Co-wide assessment grant), NYS Department of Conservation (DEC), NYS Brownfield Opportunity Area (BOA) Implementation Grant |  | H |  | X
3 | Establish funding mechanisms for remediation funding. | Partner with local organizations, such as the Jefferson County Economic Development (JCED), to establish funding mechanisms (i.e., a revolving loan fund) to encourage environmental remediation and redevelopment of strategic sites. | DRC | JCED, EPA, NYS Department of State (DOS) | JCED, NCREDC, USEPA, NYS DEC, NYS BOA Implementation Grant |  | H
4 | Continue to partner with NYS Department of State (NYS DOS). | Secure BOA designation and work with NYSDOS to develop an Implementation Strategy for the BOA study and its recommendations to: • continue and/or initiate further redevelopment activities. • secure additional funding and technical resources for implementation. • identify necessary engineering and planning documents to make selected sites shovel-ready for private/public investments. | Village of Deferiet and/or Town of Wilna | NYS DOS, DRC | NYS DOS BOA Implementation Grant | H |  |  | X
5 | Establish an Interagency Working Group (IAWG). | Establish an Interagency Working Group (IAWG) to provide a forum for state and federal agencies to meet and provide financial, administrative, and technical assistance to the village for the revitalization of the Deferiet BOA. | Tug Hill Commission | DRC, NYS DEC, EPA, NYS Department of Transportation (DOT), Jefferson County, NYS Environmental Facilities Corporation (EFC) |  | H |  |  | X
6 | Develop a village-wide resiliency plan. | Develop a village-wide resiliency plan in collaboration to assess physical risks (e.g., flooding, disease) as well as environmental (e.g., climate change, pollution), socio-political (e.g., inequity), and economic risks (e.g., high costs) that threaten quality of life in Deferiet. | Village of Deferiet | NYS DEC, JCED, Jefferson County Emergency Management Office, NYS Agencies, Public Health and Safety Departments, DPW, community organizations | NYSDOS LWRP, NYS DEC, Climate Smart Communities Grants, NYS DOS, NYSERDA, NYS DPA, US EPA, FEMA, HUD, US DOE, Foundations, Research Institutions |  | L |  |  | Coordinate with County Hazard Mitigation Plan
Goal 2: Decrease environmental threats to the Black River and protect the waterfront for future generations.
7 | Monitor Federal Energy Regulatory Commission (FERC) licensing of hydro facilities to integrate recreational facilities. | Hydropower Recreation Assistance is available from FERC to meet present and future outdoor recreation and river conservation needs; to maintain and enhance a project's riparian areas. Proposed project should have clear opportunity to enhance recreation and lead to tangible conservation of significant natural and cultural resources. | Village of Deferiet | Federal Energy Regulatory Commission (FERC) | FERC |  |  |  | X
Policy Area 2: Physical
Goal 1: Recognize the Paper Mill’s unique role in the founding of Deferiet as an innovative and dynamic mill village.
8 | Implement the 2023 Restore NY grant. | Implement the 2023 Restore NY grant awarded to Jefferson County (JC) to demolish the former St. Regis paper mill in the Village of Deferiet and create a site with a goal to create multiple community-informed projects. | JC and DRC | Village | Restore NY, NYS BOA | H
9 | Prepare a targeted Market Feasibility Study/Reuse Plan and Master Plan for Deferiet Redevelopment Corporation (DRC)- owned lands. | Prepare one study that includes a market feasibility/reuse plan and a Master Plan for Redevelopment for the former St. Regis Paper Mill and former general store/Post Office building. | DRC | Village | Restore NY, NYS BOA | H
10 | Partner with GHD Consulting to explore low-impact uses for the bark pile. | Partner with GHD to explore low impact uses for the bark pile, including but not limited to trails, look out areas, and solar (that doesn't pierce the cap). | DRC | GHD, Village |  |  | M |  |  | Confirm company name
11 | Explore creating a historic district at the former St. Regis Paper Mill. | Work with NYS State Historic Preservation Office (SHPO) to establish a historic district and celebrates the village's history as a mill town. | Local residents | NY State Historic Preservation Office (SHPO), Jefferson County Historian | NY State Historic Preservation Office (SHPO) |  |  | M
12 | Install mill-themed public art. | The installation of public art throughout the Deferiet BOA is an investment in place-making that will benefit all residents and visitors, growing the local reputation as an arts and culture destination. The village would establish a funding program to kickstart a public arts program to commission public art through a formal, participatory process, to install public art, including murals, and to provide art grants. | Local residents | Jefferson County Historian/Historical Society | NYS DOS BOA, NYSCA |  |  | L |  | JC Historical Society Paper Exhibit?
Goal 2: Develop opportunities to connect the Black River with surrounding natural resources and neighboring communities.
13 | Prepare Boat Launch Expansion Plan to enhance access to the Black River. |  | DRC | Village of Deferiet, NYS DEC, U.S. EPA, NYS DOT, NYS EFC |  |  | H
14 | Develop a Bicycle and Pedestrian Multi-Use Trails Master Plan. | The village should conduct a comprehensive analysis of bicycle and pedestrian needs and opportunities, including preliminary feasibility assessments and design work guided by input from the public. The master plan will provide a prioritized list of actions to improve the walkability and bikeability of the village. Potential actions include bike lanes, new and improved pedestrian walkways and crosswalks, multi-modal signage, bike racks, street furniture, pedestrian lighting, street trees, landscaping, and pocket-parks. | Tug Hill Commission | Village, DRC, NYS DEC, U.S. EPA, NYS DOT, NYS EFC | NYS DOS, NYS DOT |  | H |  |  | Part of Master Plan (#5)
Goal 3: Improve the image of Deferiet through physical enhancement.
15 | Design and implement gateway enhancements. | Identify suitable locations for village gateways and develop concepts for design and implementation. Gateways are areas where visitors experience a critical first impression of a community. Pleasing, welcoming gateways with quality landscaping and signage entice those travelling through to stop and explore. The BOA Steering Committee identified the need for gateway enhancements at the School Triangle property. | Village of Deferiet | Local Residents | NYS DOS BOA |  | M
16 | Update wayfinding and directional signage within the BOA to reinforce connections between historic, cultural and recreational resources. | Wayfinding and directional signage are community assets that connect residents and visitors to key destinations while improving the attractiveness of a place. The Village of Deferiet should update its wayfinding and directional signage within the BOA to reinforce connections between historic, cultural and recreational resources, and facilitate enhanced public access to the downtown. The signage could indicate walk time rather than distance. | Village of Deferiet | Tug Hill Commission | NYS DOS |  | M
17 | Develop park enhancement plans: Veterans Memorial/Pocket Park Baseball Field enhancements/reuse, and Millich Park. | The village should develop park enhancement plans that identify phased improvements to the baseball field, Millich Park, and creation of Veteran's Memorial/Pocket Park near Village Hall. Park enhancements are key to achieving a vibrant four-season Adirondack destination attracting families, businesses and visitors.” | Village of Deferiet | Village DPW, Ft. Drum | NYS DOS, NYS Office of Parks, Recreation, and Historic Preservation (OPRHP) | H
Policy Area 3: Planning/Social/Community
Goal 1: Ensure land use regulations support the vision.
18 | Undertake a Dissolution Study to potentially dissolve the Village of Deferiet into the Town of Wilna. |  | Village of Deferiet | Town of Wilna, Tug Hill Commission | NYS DOS Local Government Efficiency Grant
19 | Review and update zoning. | State law requires zoning regulations (i.e., local law, ordinance) to be adopted in accordance with a comprehensive plan in towns and villages. A BOA Nomination Study can form the legal justification for zoning and land use regulations, which in turn should be designed to implement the goals and policies set forth in these plans. The Village of Deferiet should evaluate current zoning evaluation and make changes that will allow implementation of the recommendations identified in the BOA Nomination Study. Particular attention should be given to the former St. Regis Paper Mill. Green infrastructure practices such as Low Impact Design (LID) requirements should also be further integrated into the zoning code. | Village of Deferiet | Tug Hill Commission | NYS DOS Smart Growth Program; Tug Hill Commission (technical assistance) | H
Goal 2: Create safe and stable neighborhoods.
20 | Explore and market residential infill opportunities. |  | DRC | Local developers |  |  | M
Goal 3: Integrate sustainable practices in redevelopment opportunities.
21 | Incorporate green infrastructure (bioswales, rain gardens, etc.) into private and public development projects. | As public and private development projects are undertaken Green Infrastructure practices should be integrated as a way to treat stormwater including bioswales, rain gardens, and porous pavements. These elements can be integrated into the draft zoning ordinance if completed, including the soil and erosion control section and Siting Guidelines Booklet. | Village of Deferiet | DOS | DOS BOA Implementation | H
22 | Become a Certified Climate Smart Community (CSC). | The NYS Climate Smart Communities (CSC) program supports local governments to reduce greenhouse gas emissions, adapt to a changing climate, and thrive in a green economy. Benefits include: • Greater energy independence, security, and cost savings • Healthier, more walkable urban centers with improved air quality • Conservation of green spaces for recreation and biodiversity • Reduction of future flood risk • Investment in an economy that supports sustainability and green businesses. • Engagement with residents on the future of their hometowns. | Village of Deferiet | Jefferson County, NYS DEC Climate Smart Communities, Tug Hill Commission, ANCA (circuit rider) | NYS DEC Climate Smart Communities, Jefferson County | M
Policy Area 4: Economic Development
Goal 1: Retain existing and attract new businesses to the Deferiet BOA.
23 | Prepare a 'Business Plan' for the DRC to oversee the redevelopment of Mill Properties. | As a subcommittee of the JCLDC the DRC should have its own mission and steps to complete the redevelopment of the former mill properties. This should include a budget using revenue generated from the ground lease program.
24 | Partner with NYSERDA to prepare a Renewable Energy Feasibility Study. | A renewable energy feasibility study assesses the technical, economic, social, and environmental aspects of potential renewable energy projects, including but not limited to solar, wind, biomass, geothermal, and fuels cells. | Village of Deferiet | NYSERDA | NYSERDA |  | M
Goal 2: Increase the village’s tax base and job opportunities.
25 | Continue to acquire and remediate properties. | Local development corporations (LDCs) are private, not-for-profit corporations often created by, or for the benefit of, local governments for economic development or other public purposes. LDCs, as well as certain other types of private entities (e.g., limited liability companies), are being utilized with increasing frequency by counties, cities, towns, villages, and fire districts to finance local government operations and projects. In many instances, these entities are used to avoid constitutional or statutory provisions that would apply to projects undertaken directly by a local government (e.g., prohibition on gifts to private entities, referendum requirements, competitive bidding, and limitations on the issuance of debt). - from the Office of the NYS Comptroller. | DRC | Village, Town, residents |  | H |  |  | X
26 | Partner with federal, state and local agencies to educate the public and potential developers about different funding incentives. | Partner with federal, state and local agencies to educate the public and potential developers about different funding incentives including, but not limited to: • Utilize Brownfield Cleanup Program (BCP) where appropriate • Historic Tax Credits • Low Income Housing Tax Credits | DRC | Deferiet LDC | NYS BOA, NYS ESD (Empire State Development) | M |  |  | X
Goal 3: Explore ways to leverage and promote Deferiet’s natural resources, including the Black River, for environmentally sustainable economic development.
27 | Prepare a Market Feasibility Study to become an Outdoor Recreation and Tourism destination. | The Village of Deferiet holds vast opportunities for outdoor recreation and sustainable tourism. A market feasibility study would inform the village, town, and county about the possible types and diversity of outdoor recreation and tourism amenities needed to enhance quality of life for residents and attract Fort Drum soldiers and their families to Deferiet. | DRC | Fort Drum, local Chambers of Commerce, Local Tourism Council | NYS DOS BOA Implementation Grant, Market NY |  | M

## DRC Next Steps
DRC Next Steps |  | Notes
1 | Prepare Business Plan and Budget
2 | Hire PT Staff (or use JCLDC staff)
3 | Seek BOA Implementation Grant for Detailed DRC-owned Master Plan | Village or Town must be the applicant (2026)
4 | Prepare a targeted Market Feasibility Study/Reuse Plan Master Plan/Fiscal Impact Analysis for DRC-owned lands
- Begin with identified opportunities in BOA Nomination Study and General Framework Plan
- Consider integrating Brownfield Tax Credits, Historic Tax Credits, and Housing Tax Credits in Market Study
5 | Establish Ground Lease Program to generate revenue
6 | Establish InterAgency Working Group and schedule 2-4/meetings per year
7 | Obtain EPA Assessment Funding
Ongoing
Coordinate with DANC on implementing the RESTORE grant